## Sheet2
Project schedule for the SkyView product
Categories | Tasks | Start Date | Days Needed | Completion | Actual days
Initiation | Project Initiation | 2023-09-15 | 20 | 2023-10-13 | 28
| Requirements Gathering | 2023-10-13 | 20 | 2023-11-10 | 28
| Design and Architecture | 2023-11-10 | 20 | 2023-12-08 | 28
| Cloud Infrastructure Setup | 2023-12-08 | 12 | 2023-12-26 | 18
Development | Backend Development | 2023-12-26 | 14 | 2024-01-15 | 20
| Frontend Development | 2024-01-08 | 14 | 2024-01-26 | 18
| Testing and Quality Assurance | 2024-01-22 | 10 | 2024-02-05 | 14
| Deployment | 2024-02-01 | 9 | 2024-02-14 | 13
Testing | Final Testing and Bug Fixing | 2024-02-14 | 3 | 2024-02-19 | 5
Documentation | Documentation | 2024-02-19 | 7 | 2024-02-28 | 9
Marketing | Pre-Launch Marketing and Promotion | 2024-02-28 | 7 | 2024-03-08 | 9
Launch | Launch | 2024-03-08 | 2 | 2024-03-12 | 4
Formulas:
Completion = WORKDAY([Start Date],[Days Needed])
Start Date = WORKDAY([Start Date, row above],[Days Needed, row above])
Milestone Dependencies